## Cover Report
[13 empty] | Project Title | : | Integrated Management Dashboard Production & Project Zona 13
|  |  |  | DOCUMENT REPORT | [7 empty] | Up Date Every Week | Doc Name | : | W2026I-DNGF-EM-100-PRG-WLY
Project Title Integrated Management Dashboard Production & Project Zona 13 | [5 empty] | Document No. | : | W2026I-DNGF-EM-100-PRG-WLY-0012 |  |  |  |  | Doc No | : | 12
Contract Number 901407233 | [5 empty] | SPK/ CTR Title | : | - |  |  |  |  | Doc-togle | : | 0000
Author's Organization Project | [5 empty] | Period | : | 29 Juni 2026 - 05 Juli 2026 |  |  |  |  | Doc-Concate | : | W2026I-DNGF-EM-100-PRG-WLY-0012
[6 empty] | Revision No. | : | 0 | Date | : | 2026-07-05
[13 empty] | Start Period | : | 2026-06-29
[13 empty] | End Period | : | 2026-07-05
[13 empty] | Period-Concate | : | 29 Juni 2026 - 05 Juli 2026
WEEKLY REPORT
Integrated Management Dashboard Production & Project Zona 13
Approval Sheet
| Name |  |  | Tittle |  |  | Date |  |  | Signature
| Wahyudi |  |  | Manager Project PEP Zona 13
| Seno Widjojo |  |  | Sr Engineer Project & Safety
| Andik Yuli Wahyono |  |  | Sr Engineer Construction
| Erikson Juanda Panjaitan |  |  | Sr Engineer Project Economics & Risk
| Nyoman Ading Widiartama |  |  | Sr Project Budget & Cost Control PEP Zona 13
| Bambang Saefu |  |  | Sr Engineering Project Planning & Schedulling
| Abdurahmman Hadiwijaya |  |  | Sr. Engineer Project Contract Management PEP Zona 13
Revision Status
| Rev | Issue Date | ITS PTN BH |  |  |  | Issue Porpose
|  |  | Prepared |  | Checked | Approved
| 0 | 2026-07-05 | AR |  | BS | ES | Issued for Information
Note on K2: Adinda Riana: Logo Kontraktor
Note on B3: Adinda Riana: Judul Project Sesuai dengan Judul Kontrak
Note on M3: Adinda Riana: nomor dokumen weekly di mulai dari 0001 sampai seterusnya
Note on B4: Adinda Riana: Nomor kontrak Pekerjaan
Note on M5: Adinda Riana: Periode Weekly
Note on P6: Adinda Riana: Tanggak Submittd dokumen weekly
Note on C12: Adinda Riana: Judul Sesuai dengan Kontrak apabil tidak ada SPK
Note on H30: Adinda Riana: Nama Kontraktor. Tanda tangan kontraktor sebelum di submit ke PEP

## TOC
PERTAMINA EP
|  |  | Project Title : |  | Document Number :
|  |  | Integrated Management Dashboard Production & Project Zona 13 |  | W2026I-DNGF-EM-100-PRG-WLY-0012
|  |  | Document Title: |  | Page ii
Weekly Report
Table of Content
| Cover |  |  |  |  | i
| Table of Content |  |  |  |  | ii
| Executive Summary |  |  |  |  | iii
| Area of Concern / Issues and Mitigation Plan |  |  |  |  | iii
| Master Deliverable Register |  |  |  |  | iii
Document Issued in This Week 01
Appendices
| Appendix A | Project S-Curve
| Appendix B | Master Deliverable Register
| Appendix C | Document Submitted in Week 01
| Appendix D | Activity Documentation
ELECTRICAL & INSTRUMENTATION ENGINEERING (as of 2 October)
[7 empty] | 91.76% | 84.94%
100%
[7 empty] | 91.21% | 89.34%
68.5%

## Exe Sum
PERTAMINA EP
|  |  |  | Project Title : | [9 empty] | Document Number : | [7 empty] | Doc | : | 12 |  | Previous |  |  |  |  | This Week |  |  |  |  | To Date
|  |  |  | Integrated Management Dashboard Production & Project Zona 13 | [9 empty] | W2026I-DNGF-EM-100-PRG-WLY-0012 | [7 empty] | Project Name | : | Integrated Management Dashboard Production & Project Zona 13 |  | Plan | Recovery | Actual | Variance | Variance to Recovery | Plan | Recovery | Actual | Variance | Variance to Recovery | Plan | Recovery | Actual | Variance | Variance to Recovery
|  |  |  | Document Title: | [9 empty] | Page iii | [7 empty] | Start Date | : | 2026-06-29 | 1 | 100% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 100%
|  |  |  | Weekly Report | [17 empty] | End Date | : | 2026-07-05 | 2 | 100% | 0% | 0% | -100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | -100% | 0%
[22 empty] | Progress Plan | : | 85.97% | 3 | 97.48% | 0% | 100% | 2.525% | 100% | 2.525% | 0% | 0% | -2.525% | 0% | 100% | 0% | 100% | 0% | 100%
[22 empty] | Actual Plan | : | 86.67% | 4 | 100% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 100%
Executive Summary | [21 empty] | Variance | : | 0.695% | 5 | 83.33% | 16.67% | 100% | 16.67% | 83.33% | 16.67% | 0% | 0% | -16.67% | 0% | 100% | 16.67% | 100% | 0% | 83.33%
[22 empty] | Recovery | : | 3.09% | 6 | 32.44% | 0% | 55% | 22.56% | 55% | 22.56% | 0% | 18.75% | -3.811% | 18.75% | 55% | 0% | 73.76% | 18.75% | 73.76%
1. | Executive Summary
Integrated Management Dashboard Production & Project Zona 13 progress this week (cut-off date : 05 Juli 2026) : planned cumulative progress plan is 85.98% against the actual cumulative progress of 86.67%. The progress for this week is behind the schedule 3.09%
Exe sum
Integrated Management Dashboard Production & Project Zona 13
| The detailed breakdown of the discipline weekly summary is presented in the following table. | [22 empty] | progress this week (cut-off date : 05 Juli 2026) :
planned cumulative progress plan is 85.98%
| Table 1.1 Discipline Weekly Summary | [22 empty] | against the actual cumulative progress of 86.67%.
The progress for this week is behind the schedule 3.09%
| No | Description | WF | Previous Week (Cumulative) |  |  |  |  | This Week |  |  |  |  | To Date (Cumulative) |  |  |  |  | Remarks
|  |  |  | Plan | Recovery | Actual | Variance | Variance to Recovery | Plan | Recovery | Actual | Variance | Variance to Recovery | Plan | Recovery | Actual | Variance | Variance to Recovery |  |  |  | MDR
See Appendix B for the full Master Deliverable Register (MDR) with updated dates as of 05 Juli 2026
| 1 | Analisis Kebutuhan | 9.27% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0%
| 2 | Pengadaan | 5.15% | 100% | 0% | 0% | -100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | -100% | 0% | Menunggu Keputsan dari Pertamina terkait dengan pengadaan Hardware
| 3 | Desain UI/UX | 17.33% | 97.48% | 0% | 100% | 2.525% | 0% | 2.525% | 0% | 0% | -2.525% | 0% | 100% | 0% | 100% | 0% | 0%
| 4 | Integrasi Sumber Data; Konfigurasi database dengan sumber data; Data Connection Schema & Production Data Mapping | 18.54% | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0%
| 5 | Persiapan Data (ETL) | 18.54% | 83.33% | 0% | 100% | 16.67% | 0% | 16.67% | 0% | 0% | -16.67% | 0% | 100% | 0% | 100% | 0% | 0%
| 6 | Pengembangan Dashboard | 31.17% | 32.44% | 0% | 55% | 22.56% | 0% | 22.56% | 0% | 18.75% | -3.811% | 0% | 55% | 0% | 73.76% | 18.75% | 0% | Menunggu Keputsan dari Pertamina untuk kelanjutannya
|  | Overall | 100% | 75.41% | 0% | 80.83% | 5.411% | 0% | 10.56% | 0% | 5.845% | -4.716% | 0% | 85.97% | 0% | 86.67% | 0.695% | 0%
| * | The S-Curve can be seen in Appendix-A
2. | Area of Concern / Issues and Mitigation Plan
1. Pertamina dapat mulai melakukan review terhadap dashboard yang telah dikembangkan oleh ITS 2. Dokumen 6d sedang dalam review oleh Pak Seno. 3. Data AIRMS dan I2AIMS yang digunakan di modul OSF adalah data dummy. Jika terdapat data yang baru disampaikan, dapat di lakukan pada fase berikutnya (Post Implementation). 4. Untuk modul Project, saat ini masih ada contoh NBD (Project dengan ITS), untuk contoh Project BD belum ada.
3. | Master Deliverable Register
See Appendix B for the full Master Deliverable Register (MDR) with updated dates as of 05 Juli 2026
4. | Document Issued in This Week
| Week | : 12
| Start Date | : 29 Juni 2026
| End Date | : 05 Juli 2026
The list submitted document is provided in Appendix C
ELECTRICAL & INSTRUMENTATION ENGINEERING (as of 2 October)
[20 empty] | 91.76% | 84.94%
100%
[20 empty] | 91.21% | 89.34%
68.5%

## Appendix A
PERTAMINA EP
| Project Title : |  | Document Number :
| Integrated Management Dashboard Production & Project Zona 13 |  | W2026I-DNGF-EM-100-PRG-WLY-0012
| Document Title: |  | Appendix A
Weekly Report
APPENDIX A
PROJECT S-CURVE
ELECTRICAL & INSTRUMENTATION ENGINEERING (as of 2 October)
ELECTRICAL & INSTRUMENTATION ENGINEERING (as of 2 October)
[5 empty] | 91.76% | 84.94%
100%
[5 empty] | 91.21% | 89.34%
68.5%

## S-Overall
ITS PTN BH
S - CURVE - OVERALL
CLIENT | : | PT Pertamina EP
PROJECT | : | Integrated Management Dashboard Production & Project Zona 13
WO Ttile. | : | W2026I-DNGF-EM-100-PRG-WLY
WO No. | : | W2026I-DNGF-EM-100-PRG-WLY-0012
[25 empty] | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[25 empty] | 2026-04-01 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | 2026-07-12 | 2026-07-19 | 2026-07-26 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-31
[24 empty] | ACTUAL THIS WEEK | 0% | 21.77% | 14.41% | 5.701% | 1.876% | 1.545% | 5.959% | 0.9425% | 3.089% | 6.227% | 8.031% | 8.186% | 3.09% | 5.845%
[24 empty] | ACTUAL CUMMULATIVE | 0% | 21.77% | 36.18% | 41.88% | 43.76% | 45.3% | 51.26% | 52.2% | 55.29% | 61.52% | 69.55% | 77.73% | 80.83% | 86.67%
[24 empty] | PLAN THIS WEEK | 0% | 6.336% | 3.709% | 7.108% | 4.259% | 4.895% | 12.26% | 8.823% | 8.418% | 3.348% | 9.579% | 5.778% | 0.9045% | 10.56% | 0% | 5.845% | 2.335% | 5.845% | 0% | 0% | 0% | 0%
[24 empty] | PLAN CUMMULATIVE | 0% | 6.336% | 10.04% | 17.15% | 21.41% | 26.31% | 38.56% | 47.39% | 55.81% | 59.15% | 68.73% | 74.51% | 75.41% | 85.97% | 85.97% | 91.82% | 94.16% | 100% | 100% | 100% | 100% | 100%
[24 empty] | Recovery | 0% | 0% | 0% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09%
[24 empty] | VARIANCE TO Recovery | 0% | 21.77% | 36.18% | 38.79% | 40.67% | 42.21% | 48.17% | 49.11% | 52.2% | 58.43% | 66.46% | 74.64% | 77.73% | 83.58%
[24 empty] | VARIANCE TO PLAN | 0% | 15.44% | 26.13% | 24.73% | 22.34% | 18.99% | 12.7% | 4.815% | -0.514% | 2.365% | 0.817% | 3.225% | 5.411% | 0.695%
OPF Balongan - Adequacy Check
DESCRIPTION |  | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  | 2026-04-01 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | 2026-07-12 | 2026-07-19 | 2026-07-26 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-31
PLANNED |  | 0% | 0% | 0% | 3.95% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9% | 103.9%
ACTUAL THIS WEEK |  | 0% | 21.77% | 14.41% | 5.701% | 1.876% | 1.545% | 5.959% | 0.9425% | 3.089% | 6.227% | 8.031% | 8.186% | 3.09% | 5.845%
ACTUAL CUMMULATIVE |  | 0% | 21.77% | 36.18% | 41.88% | 43.76% | 45.3% | 51.26% | 52.2% | 55.29% | 61.52% | 69.55% | 77.73% | 80.83% | 86.67%
PLAN THIS WEEK |  | 0% | 6.336% | 3.709% | 7.108% | 4.259% | 4.895% | 12.26% | 8.823% | 8.418% | 3.348% | 9.579% | 5.778% | 0.9045% | 10.56% | 0% | 5.845% | 2.335% | 5.845% | 0% | 0% | 0% | 0%
PLAN CUMMULATIVE |  | 0% | 6.336% | 10.04% | 17.15% | 21.41% | 26.31% | 38.56% | 47.39% | 55.81% | 59.15% | 68.73% | 74.51% | 75.41% | 85.97% | 85.97% | 91.82% | 94.16% | 100% | 100% | 100% | 100% | 100%
Recovery | bar: 2026-04-01 to 2026-07-05
VARIANCE TO Recovery | bar: 2026-04-01 to 2026-07-05
VARIANCE TO PLAN |  | 0% | 15.44% | 26.13% | 24.73% | 22.34% | 18.99% | 12.7% | 4.815% | -0.514% | 2.365% | 0.817% | 3.225% | 5.411% | 0.695%
ENGINEERING PROGRESS S-CURVE

## Check
| Exe Sum | S-Curve
Previous (Cummulative)
Plan | 75.41% | 75.41% | Sesuai
Aktual | 80.83% | 80.83% | Sesuai
Variance | 5.411% | 5.411% | Sesuai
This Week
Plan | 10.56% | 10.56% | Sesuai
Aktual | 5.845% | 5.845% | Sesuai
Variance | -4.716% | -4.716% | Sesuai
To Date (Cummulative)
Plan | 85.97% | 85.97% | Sesuai
Aktual | 86.67% | 86.67% | Sesuai
Variance | 0.695% | 0.695% | Sesuai

## Appendix B
PERTAMINA EP
| Project Title : |  | Document Number :
| Integrated Management Dashboard Production & Project Zona 13 |  | W2026I-DNGF-EM-100-PRG-WLY-0012
| Document Title: |  | Appendix B
Weekly Report
APPENDIX B
MASTER DELIVERABLE REGISTER (MDR)
ELECTRICAL & INSTRUMENTATION ENGINEERING (as of 2 October)
ELECTRICAL & INSTRUMENTATION ENGINEERING (as of 2 October)
[5 empty] | 91.76% | 84.94%
100%
[5 empty] | 91.21% | 89.34%
68.5%

## Overall MDR_
ENGINEERING DOCUMENTS REGISTER
| CLIENT | : | PT Pertamina EP | [35 empty] | Rev. No. : | 0
| PROJECT | : | Integrated Management Dashboard Production & Project Zona 13 | [35 empty] | Week No. : | 12 | [14 empty] | 2026-07-05 | Report No. | 12 | [45 empty] | 2026-07-05 | Report No. | 12
| WO Title | : | [36 empty] | Cut-off Date : | 2026-07-05 | [14 empty] | 2026-06-29 |  | 11 | [45 empty] | 2026-06-29 |  | 11
| WO No. | :
[55 empty] | ESTIMATE PLAN CUMULATIVE REV.0 | [23 empty] | ESTIMATE FORECAST CUMULATIVE REV.0 | [23 empty] | ACTUAL CUMULATIVE REV.0
|  |  |  | REVISION | WEIGHT FACTOR |  | Inter-Discipline Review |  |  | Rev A |  |  |  | Rev A |  |  |  | Rev 0 | [8 empty] | APPROVED |  |  |  |  | PHYSICAL PROGRESS | [14 empty] | Activity | ACTUAL |  | PLAN |  | FORECAST
[10 empty] | IFR (Issued for Review) |  |  |  | IFR (Issued for Review) |  |  |  | IFD (Issued for Design) |  |  |  | Close Out Report | [7 empty] | Progress Overall | [12 empty] | PAYMENT PROGRESS
Deliverables | [6 empty] | 5% |  |  | 25% |  |  |  | 50% |  |  |  | 75% |  |  |  | 100% | [9 empty] | EACH DELIVERABLE | [6 empty] | OVERALL |  |  |  | OVERALL |  |  |  |  | LAST | TODATE | LAST | TODATE | LAST | TODATE |  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[7 empty] | 5% | 5% | 5% | 25% | 25% | 25% | 25% | 50% | 50% | 50% | 50% | 75% | 75% | 75% | 75% | 100% | 100% | 100% | 100% | 100% |  |  |  |  | Doc Impact | ACTUAL |  |  | PLAN | Re-baseline | VARIANCE PLAN | VARIANCE Re-baseline | ACTUAL | PLAN | Re-baseline | VAR | LAST WEEK | THIS WEEK | TODATE | [10 empty] | 2026-04-01 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | 2026-07-12 | 2026-07-19 | 2026-07-26 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-31 |  |  | 2026-04-01 | 2026-04-13 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | 2026-07-12 | 2026-07-19 | 2026-07-26 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-31 |  |  | 2026-04-01 | 2026-04-13 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | 2026-07-12 | 2026-07-19 | 2026-07-26 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-31
[7 empty] | Plan | Recovery | Actual | Plan | Recovery | Actual | Return | Plan | Recovery | Actual | Return | Plan | Recovery | Actual | Return | Plan | Recovery | Actual | Return | NOTE | Plan | Forecast | Actual |  |  | LAST | THIS WK | TODATE | TODATE | TODATE | TODATE |  | TODATE | TODATE | TODATE | TODATE |  |  | W. U .
OVERALL |  |  |  |  | 100% | [40 empty] | 77.74% | OVERALL | 83.16% | 86.67% | 75.41% | 85.98% | 3.09% | 3.09% |  |  | 0 | 0.063355 | 0.10045 | 0.17153 | 0.21412 | 0.26307 | 0.38565 | 0.47388 | 0.55805 | 0.59153 | 0.68732 | 0.7451 | 0.75414 | 0.85975 | 0.85975 | 0.9182 | 0.94155 | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.069525 | 0.069525 | 0.069525 | 0.069525 | 0.069525 | 0.069525 | 0.069525 | 0.069525 |  |  | 0 | 0.21773 | 0.36179 | 0.4188 | 0.43756 | 0.45301 | 0.5126 | 0.52202 | 0.55291 | 0.61518 | 0.69549 | 0.77735 | 0.80825 | 0.8667 | 0.8667 | 0.8667 | 0.8667 | 0.8667 | 0.8667 | 0.8667 | 0.8667 | 0.8667
1 |  | Analisis Kebutuhan |  |  | 9.27% | [40 empty] | 9.27% | 1 | 9.27% | 9.27% | 9.27% | 9.27% | 0% | 0% |  |  | 0 | 0.04635 | 0.069525 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.069525 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927
1.a | W2026I-DNGF-EM-100-PRD-SPC-0001 | Dokumentasi BRD |  |  | 4% |  | 2026-04-01 |  | 2026-04-01 | 2026-04-06 |  | 2026-04-02 |  | 2026-04-11 |  | 2026-04-06 |  | 2026-04-16 |  | 2026-04-13 |  | 2026-04-21 |  | 2026-04-19 | [5 empty] | 4% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 4% | 4% | 0% | 0% |  |  |  | 4% | 1.a | 4% | 4% | 4% | 4% | 0% | 0% |  |  | 0 | 0.02 | 0.03 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.03 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04
1.b | W2026I-DNGF-EM-100-PRD-SPC-0002 | Dokumentasi Awal Hasil Wawancara |  |  | 5.27% |  | 2026-04-01 |  | 2026-04-01 | 2026-04-06 |  | 2026-04-02 |  | 2026-04-11 |  | 2026-04-06 |  | 2026-04-16 |  | 2026-04-13 |  | 2026-04-21 |  | 2026-04-19 | [5 empty] | 5.27% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 5.27% | 5.27% | 0% | 0% |  |  |  | 5.27% | 1.b | 5.27% | 5.27% | 5.27% | 5.27% | 0% | 0% |  |  | 0 | 0.02635 | 0.039525 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.039525 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527 | 0.0527
2 |  | Pengadaan |  |  | 5.15% | [40 empty] | 0% | 2 | 0% | 0% | 5.15% | 5.15% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.002575 | 0.02575 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038625 | 0.038625 | 0.038625 | 0.038625 | 0.038625 | 0.038625 | 0.038625 | 0.038625 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a |  | Pengadaan Hardware |  |  | 5.15% |  | 2026-05-17 | 2026-07-07 |  | 2026-05-20 12:00 | 2026-07-07 |  |  | 2026-05-24 | 2026-07-07 |  |  | 2026-05-27 12:00 | 2026-07-07 |  |  | 2026-05-31 | [7 empty] | 0% |  | 0% | 0% | 0% | 100% | 0% | -100% | 0% | 0% | 5.15% | 0% | -5.15% |  |  |  | 0% | 2.a | 0% | 0% | 5.15% | 5.15% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.002575 | 0.02575 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 | 0.0515 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038625 | 0.038625 | 0.038625 | 0.038625 | 0.038625 | 0.038625 | 0.038625 | 0.038625 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Desain UI/UX |  |  | 17.33% | [40 empty] | 17.33% | 3 | 17.33% | 17.33% | 16.89% | 17.33% | 0% | 0% |  |  | 0 | 0.010825 | 0.02165 | 0.032475 | 0.048925 | 0.071425 | 0.09955 | 0.12768 | 0.1558 | 0.15667 | 0.16017 | 0.16455 | 0.16892 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.10185 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733 | 0.1733
3.a | W2026I-DNGF-EM-100-PRD-SPC-0003 | User Flow & Wireframe (Low-Fidelity) |  |  | 4.33% |  | 2026-04-01 |  | 2026-04-01 | 2026-04-08 06:00 |  | 2026-04-05 |  | 2026-04-15 12:00 |  | 2026-04-07 |  | 2026-04-22 18:00 |  | 2026-04-10 |  | 2026-04-30 |  | 2026-04-14 | [5 empty] | 4.33% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 4.33% | 4.33% | 0% | 0% |  |  |  | 4.33% | 3.a | 4.33% | 4.33% | 4.33% | 4.33% | 0% | 0% |  |  | 0 | 0.010825 | 0.02165 | 0.032475 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.032475 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433 | 0.0433
3.b | W2026I-DNGF-EM-100-PRD-SPC-0004 | Design System & High-Fidelity Mockup |  |  | 11.25% |  | 2026-05-01 |  | 2026-04-01 | 2026-05-08 12:00 |  | 2026-04-05 |  | 2026-05-16 |  | 2026-04-07 |  | 2026-05-23 12:00 |  | 2026-04-19 |  | 2026-05-31 |  | 2026-04-14 | [5 empty] | 11.25% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 11.25% | 11.25% | 0% | 0% |  |  |  | 11.25% | 3.b | 11.25% | 11.25% | 11.25% | 11.25% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0.005625 | 0.028125 | 0.05625 | 0.084375 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.05625 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125 | 0.1125
3.c | W2026I-DNGF-EM-100-PRD-SPC-0005 | Interactive Prototype & User Testing |  |  | 1.75% |  | 2026-06-01 |  | 2026-04-01 | 2026-06-08 06:00 |  | 2026-04-05 |  | 2026-06-15 12:00 |  | 2026-04-07 |  | 2026-06-22 18:00 |  | 2026-04-10 |  | 2026-06-30 |  | 2026-04-14 | [5 empty] | 1.75% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 1.75% | 1.75% | 0% | 0% |  |  |  | 1.75% | 3.c | 1.75% | 1.75% | 1.313% | 1.75% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.000875 | 0.004375 | 0.00875 | 0.013125 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.013125 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175 | 0.0175
4 |  | Integrasi Sumber Data; Konfigurasi database dengan sumber data; Data Connection Schema & Production Data Mapping |  |  | 18.54% | [40 empty] | 18.54% | 4 | 18.54% | 18.54% | 18.54% | 18.54% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0.007385 | 0.018385 | 0.050675 | 0.0876 | 0.10135 | 0.13395 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.04635 | 0.0927 | 0.10645 | 0.10645 | 0.10645 | 0.10645 | 0.11588 | 0.12962 | 0.1528 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854
4.a | W2026I-DNGF-EM-100-PRD-SPC-0006 | Integrasi Sumber Data |  |  | 9.27% |  | 2026-05-01 |  | 2026-04-05 | 2026-05-12 |  | 2026-04-12 |  | 2026-05-23 |  | 2026-04-15 |  | 2026-06-03 |  | 2026-06-01 |  | 2026-06-14 |  | 2026-06-11 | [5 empty] | 9.27% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 9.27% | 9.27% | 0% | 0% |  |  |  | 9.27% | 4.a | 9.27% | 9.27% | 9.27% | 9.27% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0.004635 | 0.004635 | 0.023175 | 0.04635 | 0.04635 | 0.069525 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.023175 | 0.04635 | 0.04635 | 0.04635 | 0.04635 | 0.04635 | 0.04635 | 0.04635 | 0.069525 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927 | 0.0927
4.b | W2026I-DNGF-EM-100-PRD-SPC-0007 | Konfigurasi database dengan sumber data |  |  | 5.5% |  | 2026-05-01 |  | 2026-04-05 | 2026-05-08 12:00 |  | 2026-04-12 |  | 2026-05-16 |  | 2026-04-15 |  | 2026-05-23 12:00 |  | 2026-04-23 |  | 2026-05-31 |  | 2026-05-31 | [5 empty] | 5.5% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 5.5% | 5.5% | 0% | 0% |  |  |  | 5.5% | 4.b | 5.5% | 5.5% | 5.5% | 5.5% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0.00275 | 0.01375 | 0.0275 | 0.04125 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.01375 | 0.0275 | 0.04125 | 0.04125 | 0.04125 | 0.04125 | 0.04125 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055
4.c | W2026I-DNGF-EM-100-PRD-SPC-0008 | Data Connection Schema & Production Data Mapping |  |  | 3.77% |  | 2026-06-01 |  | 2026-04-05 | 2026-06-04 06:00 |  | 2026-04-12 |  | 2026-06-07 12:00 |  | 2026-04-15 |  | 2026-06-10 18:00 |  | 2026-05-19 |  | 2026-06-14 |  | 2026-06-11 | [5 empty] | 3.77% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 3.77% | 3.77% | 0% | 0% |  |  |  | 3.77% | 4.c | 3.77% | 3.77% | 3.77% | 3.77% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.009425 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0.009425 | 0.01885 | 0.01885 | 0.01885 | 0.01885 | 0.01885 | 0.028275 | 0.028275 | 0.028275 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377 | 0.0377
5 |  | Persiapan Data (ETL) |  |  | 18.54% | [40 empty] | 15.45% | 5 | 18.54% | 18.54% | 15.45% | 18.54% | 3.09% | 3.09% |  |  | 0 | 0.00618 | 0.00927 | 0.04635 | 0.0618 | 0.07725 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1545 | 0.1545 | 0.1545 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 |  |  | 0 | 0 | 0 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 |  |  | 0 | 0 | 0.00309 | 0.04635 | 0.0618 | 0.07725 | 0.1236 | 0.1236 | 0.1236 | 0.1545 | 0.1545 | 0.1545 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854 | 0.1854
5.a | W2026I-DNGF-EM-100-PRD-SPC-0009 | Data Mapping |  |  | 6.18% |  | 2026-04-15 |  | 2026-04-14 | 2026-04-22 06:00 |  | 2026-04-21 |  | 2026-04-29 12:00 |  | 2026-04-28 |  | 2026-05-06 18:00 |  | 2026-05-06 |  | 2026-05-14 |  | 2026-05-14 | [5 empty] | 6.18% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 6.18% | 6.18% | 0% | 0% |  |  |  | 6.18% | 5.a | 6.18% | 6.18% | 6.18% | 6.18% | 0% | 0% |  |  | 0 | 0 | 0.00309 | 0.01545 | 0.0309 | 0.04635 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0.00309 | 0.01545 | 0.0309 | 0.04635 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0618
5.b | W2026I-DNGF-EM-100-PRD-SPC-0010 | Database yang sudah bersih, terstruktur, dan siap digunakan untuk visualisasi |  |  | 12.36% |  | 2026-04-01 | 2026-04-20 | 2026-04-20 | 2026-04-23 12:00 | 2026-04-25 | 2026-04-25 |  | 2026-05-16 |  | 2026-05-13 |  | 2026-06-07 12:00 |  | 2026-06-05 |  | 2026-06-30 |  | 2026-06-25 | [5 empty] | 12.36% |  | 100% | 0% | 100% | 100% | 25% | 0% | 75% | 12.36% | 12.36% | 3.09% | 0% |  |  |  | 9.27% | 5.b | 12.36% | 12.36% | 9.27% | 12.36% | 3.09% | 3.09% |  |  | 0 | 0.00618 | 0.00618 | 0.0309 | 0.0309 | 0.0309 | 0.0618 | 0.0618 | 0.0618 | 0.0618 | 0.0927 | 0.0927 | 0.0927 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236 |  |  | 0 | 0 | 0 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 | 0.0309 |  |  | 0 | 0 | 0 | 0.0309 | 0.0309 | 0.0309 | 0.0618 | 0.0618 | 0.0618 | 0.0927 | 0.0927 | 0.0927 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236 | 0.1236
6 |  | Pengembangan Dashboard |  |  | 31.17% | [40 empty] | 17.15% | 6 | 19.48% | 22.99% | 10.11% | 17.15% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0.00331 | 0.00331 | 0.01655 | 0.01655 | 0.0331 | 0.0331 | 0.043045 | 0.09645 | 0.10112 | 0.17145 | 0.17145 | 0.2299 | 0.25325 | 0.3117 | 0.3117 | 0.3117 | 0.3117 | 0.3117 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0.00331 | 0.00331 | 0.01655 | 0.01655 | 0.033685 | 0.041875 | 0.08959 | 0.17145 | 0.17145 | 0.2299 | 0.2299 | 0.2299 | 0.2299 | 0.2299 | 0.2299 | 0.2299 | 0.2299 | 0.2299
6.a | W2026I-DNGF-EM-100-PRD-SPC-0011 | Penyusunan sitemap dashboard, definisi hak akses menu (Role Based Access Control), dan struktur navigasi |  |  | 1.17% |  | 2026-06-08 |  | 2026-05-30 | 2026-06-11 06:00 |  | 2026-06-01 |  | 2026-06-14 12:00 |  | 2026-06-01 |  | 2026-06-17 18:00 |  | 2026-06-06 |  | 2026-06-21 |  | 2026-06-14 | [5 empty] | 1.17% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 1.17% | 1.17% | 0% | 0% |  |  |  | 1.17% | 6.a | 1.17% | 1.17% | 1.17% | 1.17% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002925 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.000585 | 0.008775 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117 | 0.0117
6.b | W2026I-DNGF-EM-100-PRD-SPC-0012 | Pengembangan Home Page |  |  | 6.62% |  | 2026-05-01 |  | 2026-05-01 | 2026-05-16 |  | 2026-05-16 |  | 2026-05-31 |  | 2026-05-30 |  | 2026-06-15 |  | 2026-06-09 |  | 2026-06-30 |  | 2026-06-14 | [5 empty] | 6.62% |  | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 6.62% | 6.62% | 0% | 0% |  |  |  | 6.62% | 6.b | 6.62% | 6.62% | 4.965% | 6.62% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0.00331 | 0.00331 | 0.01655 | 0.01655 | 0.0331 | 0.0331 | 0.0331 | 0.04965 | 0.04965 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0.00331 | 0.00331 | 0.01655 | 0.01655 | 0.0331 | 0.0331 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662 | 0.0662
6.c | W2026I-DNGF-EM-100-PRD-SPC-0013 | Pengembangan Modul & Komponen Visual |  |  | 14.04% |  | 2026-06-08 |  | 2026-06-08 | 2026-06-21 |  | 2026-06-19 |  | 2026-07-04 |  | 2026-06-19 |  | 2026-07-17 |  | 2026-07-01 |  | 2026-07-30 | [7 empty] | 10.53% |  | 50% | 25% | 75% | 50% | 0% | 25% | 75% | 10.53% | 7.02% | 0% | 3.51% |  |  |  | 7.02% | 6.c | 7.02% | 10.53% | 3.51% | 7.02% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00702 | 0.0351 | 0.0351 | 0.0702 | 0.0702 | 0.1053 | 0.1053 | 0.1404 | 0.1404 | 0.1404 | 0.1404 | 0.1404 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00702 | 0.0702 | 0.0702 | 0.1053 | 0.1053 | 0.1053 | 0.1053 | 0.1053 | 0.1053 | 0.1053 | 0.1053 | 0.1053
6.d | W2026I-DNGF-EM-100-PRD-SPC-0014 | Integrasi Data & Finalisasi Interaktivitas |  |  | 9.34% |  | 2026-06-24 |  | 2026-06-14 | 2026-07-03 06:00 |  | 2026-06-18 |  | 2026-07-12 12:00 |  | 2026-06-29 |  | 2026-07-21 18:00 |  |  |  | 2026-07-31 | [7 empty] | 4.67% |  | 50% | 0% | 50% | 25% | 0% | 25% | 50% | 4.67% | 2.335% | 0% | 2.335% |  |  |  | 2.335% | 6.d | 4.67% | 4.67% | 0.467% | 2.335% | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00467 | 0.02335 | 0.02335 | 0.0467 | 0.07005 | 0.0934 | 0.0934 | 0.0934 | 0.0934 | 0.0934 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00467 | 0.02335 | 0.02335 | 0.0467 | 0.0467 | 0.0467 | 0.0467 | 0.0467 | 0.0467 | 0.0467 | 0.0467 | 0.0467
|  |  | OVERALL PROJECT | [26 empty] | 86.67% |  | 83.16% | 3.51% | 86.67% | 85.98% | 3.09% | 0.695% | 83.58% | 86.67% | 85.98% | 3.09% | 0.695% | [5 empty] | 83.16% | 86.67% | 75.41% | 85.98% | 3.09% | 3.09%
[55 empty] | ACTIVITY | [23 empty] | ACTIVITY | [23 empty] | ACTIVITY
[55 empty] | 1 | 0% | 4.635% | 6.953% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% |  | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 1 | 0% | 6.953% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27% | 9.27%
[55 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0.2575% | 2.575% | 5.15% | 5.15% | 5.15% | 5.15% | 5.15% | 5.15% | 5.15% | 5.15% | 5.15% | 5.15% | 5.15% | 5.15% | 5.15% | 5.15% |  | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.862% | 3.862% | 3.862% | 3.862% | 3.862% | 3.862% | 3.862% | 3.862% |  | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PRD | Procedure | [53 empty] | 3 | 0% | 1.083% | 2.165% | 3.247% | 4.893% | 7.143% | 9.955% | 12.77% | 15.58% | 15.67% | 16.02% | 16.46% | 16.89% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% |  | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 3 | 0% | 10.18% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33% | 17.33%
SPC | Specification | [53 empty] | 4 | 0% | 0% | 0% | 0% | 0.7385% | 1.838% | 5.067% | 8.76% | 10.13% | 13.39% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% |  | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 4 | 0% | 4.635% | 9.27% | 10.65% | 10.65% | 10.65% | 10.65% | 11.59% | 12.96% | 15.28% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54%
DRW | Drawing | [53 empty] | 5 | 0% | 0.618% | 0.927% | 4.635% | 6.18% | 7.725% | 12.36% | 12.36% | 12.36% | 12.36% | 15.45% | 15.45% | 15.45% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% |  | 5 | 0% | 0% | 0% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% |  | 5 | 0% | 0% | 0.309% | 4.635% | 6.18% | 7.725% | 12.36% | 12.36% | 12.36% | 15.45% | 15.45% | 15.45% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54% | 18.54%
RPT | Reports | [53 empty] | 6 | 0% | 0% | 0% | 0% | 0.331% | 0.331% | 1.655% | 1.655% | 3.31% | 3.31% | 4.304% | 9.645% | 10.11% | 17.15% | 17.15% | 22.99% | 25.32% | 31.17% | 31.17% | 31.17% | 31.17% | 31.17% |  | 6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 6 | 0% | 0% | 0% | 0% | 0.331% | 0.331% | 1.655% | 1.655% | 3.369% | 4.188% | 8.959% | 17.15% | 17.15% | 22.99% | 22.99% | 22.99% | 22.99% | 22.99% | 22.99% | 22.99% | 22.99% | 22.99%
BOQ | Bill of Quantity | [5 empty] | Aktual | Plan | [46 empty] | OVERALL | 0% | 6.336% | 10.04% | 17.15% | 21.41% | 26.31% | 38.56% | 47.39% | 55.81% | 59.15% | 68.73% | 74.51% | 75.41% | 85.97% | 85.97% | 91.82% | 94.16% | 100% | 100% | 100% | 100% | 100% |  | OVERALL | 0% | 0% | 0% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 6.953% | 6.953% | 6.953% | 6.953% | 6.953% | 6.953% | 6.953% | 6.953% |  | OVERALL | 0% | 21.77% | 36.18% | 41.88% | 43.76% | 45.3% | 51.26% | 52.2% | 55.29% | 61.52% | 69.55% | 77.73% | 80.83% | 86.67% | 86.67% | 86.67% | 86.67% | 86.67% | 86.67% | 86.67% | 86.67% | 86.67%
DSH | Data Sheet |  |  |  |  | 1.a | 2026-04-19 | 2026-04-21 | 2026-04-19
CALC | Calculation |  |  |  |  | 1.b | 2026-04-19 | 2026-04-21 | 2026-04-19 | [44 empty] | WF | ACTIVITY | [22 empty] | WF | ACTIVITY | [22 empty] | WF | ACTIVITY
VDOC | Vendor Document |  |  |  |  | 2 | 0 | 0 | 0 | [44 empty] | 9.27% | 1 | 0% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 9.27% | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.27% | 1 | 0% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[6 empty] | 2.a | 0 | 2026-05-31 | 0 | [44 empty] | 5.15% | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 5.15% | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 5.15% | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[6 empty] | 3 | 0 | 0 | 0 | [44 empty] | 17.33% | 3 | 0% | 6.246% | 12.49% | 18.74% | 28.23% | 41.21% | 57.44% | 73.67% | 89.9% | 90.41% | 92.43% | 94.95% | 97.48% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 17.33% | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.33% | 3 | 0% | 58.77% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[6 empty] | 3.a | 2026-04-14 | 2026-04-30 | 2026-04-14 | [44 empty] | 18.54% | 4 | 0% | 0% | 0% | 0% | 3.983% | 9.916% | 27.33% | 47.25% | 54.67% | 72.25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 18.54% | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.54% | 4 | 0% | 25% | 50% | 57.42% | 57.42% | 57.42% | 57.42% | 62.5% | 69.92% | 82.42% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[6 empty] | 3.b | 2026-04-19 | 2026-05-31 | 2026-04-19 | [44 empty] | 18.54% | 5 | 0% | 3.333% | 5% | 25% | 33.33% | 41.67% | 66.67% | 66.67% | 66.67% | 66.67% | 83.33% | 83.33% | 83.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 18.54% | 5 | 0% | 0% | 0% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 16.67% | 18.54% | 5 | 0% | 0% | 1.667% | 25% | 33.33% | 41.67% | 66.67% | 66.67% | 66.67% | 83.33% | 83.33% | 83.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[6 empty] | 3.c | 2026-04-14 | 2026-06-30 | 2026-04-14 | [44 empty] | 31.17% | 6 | 0% | 0% | 0% | 0% | 1.062% | 1.062% | 5.31% | 5.31% | 10.62% | 10.62% | 13.81% | 30.94% | 32.44% | 55% | 55% | 73.76% | 81.25% | 100% | 100% | 100% | 100% | 100% | 31.17% | 6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 31.17% | 6 | 0% | 0% | 0% | 0% | 1.062% | 1.062% | 5.31% | 5.31% | 10.81% | 13.43% | 28.74% | 55% | 55% | 73.76% | 73.76% | 73.76% | 73.76% | 73.76% | 73.76% | 73.76% | 73.76% | 73.76%
[6 empty] | 4 | [47 empty] | 100% | OVERALL | 0% | 6.336% | 10.04% | 17.15% | 21.41% | 26.31% | 38.56% | 47.39% | 55.81% | 59.15% | 68.73% | 74.51% | 75.41% | 85.97% | 85.97% | 91.82% | 94.16% | 100% | 100% | 100% | 100% | 100% | 100% | OVERALL | 0% | 0% | 0% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 3.09% | 6.953% | 6.953% | 6.953% | 6.953% | 6.953% | 6.953% | 6.953% | 6.953% | 100% | OVERALL | 0% | 21.77% | 36.18% | 41.88% | 43.76% | 45.3% | 51.26% | 52.2% | 55.29% | 61.52% | 69.55% | 77.73% | 80.83% | 86.67% | 86.67% | 86.67% | 86.67% | 86.67% | 86.67% | 86.67% | 86.67% | 86.67%
[6 empty] | 4.a | 2026-06-11 | 2026-06-14 | 2026-06-11
[6 empty] | 4.b | 2026-05-31 | 2026-05-31 | 2026-05-31
[6 empty] | 4.c | 2026-06-11 | 2026-06-14 | 2026-06-11
5
[6 empty] | 5.a | 2026-05-14 | 2026-05-14 | 2026-05-14
[6 empty] | 5.b | 2026-06-25 | 2026-06-30 | 2026-06-25
6
[6 empty] | 6.a | 2026-06-14 | 2026-06-21 | 2026-06-14
[6 empty] | 6.b | 2026-06-14 | 2026-06-30 | 2026-06-14
[6 empty] | 6.c | 2026-07-01 | 2026-07-30 | 2026-06-19
[6 empty] | 6.d | 2026-06-29 | 2026-07-31 | 2026-06-18
Formulas:
Rev A = [Inter-Discipline Review]+(([Rev A]-[Inter-Discipline Review])*0.5)
Rev A = [Inter-Discipline Review]+(([Close Out Report]-[Inter-Discipline Review])*0.5)
Rev 0 = [Rev A]+(([Close Out Report]-[Rev A])*0.5)

## Appendix C
PERTAMINA EP
| Project Title : |  | Document Number :
| Integrated Management Dashboard Production & Project Zona 13 |  | W2026I-DNGF-EM-100-PRG-WLY-0012
| Document Title: |  | Appendix C
Weekly Report
APPENDIX C
DOCUMENT SUBMITTED IN WEEK 11
ELECTRICAL & INSTRUMENTATION ENGINEERING (as of 2 October)
ELECTRICAL & INSTRUMENTATION ENGINEERING (as of 2 October)
[5 empty] | 91.76% | 84.94%
100%
[5 empty] | 91.21% | 89.34%
68.5%

## Doc. Submitted
PERTAMINA EP
|  | Project Title : |  | Document Number : | W2026I-DNGF-EM-100-PRG-WLY-0012
Integrated Management Dashboard Production & Project Zona 13
Document Title:
Weekly Report
DOCUMENT SUBMITTED IN WEEK 11
No | Transmittal | Doc./Dwg Number |  | Deliverable |  | Date Submission | Status Document | Remarks
1 | TRM DWE-PHE ONWJ-350/001 | FOXTROT-O-RPT-1102 |  | Process Simulation Report |  | 2021-09-24 | IFR
2 | TRM DWE-PHE ONWJ-350/002 | FOXTROT-G-PHI-1101 |  | Conceptual Design Basis & Design Philosophy |  | 2021-09-24 | IFR
1 | TRM DWE-PHE ONWJ-350/003 | FOXTROT-FXEA-P-PFD-6101 |  | Process Flow Diagram (PFD) |  | 2021-10-01 | IFR
FOXTROT-FXEA-P-PFD-6101~A-1 to 2 (Option 1~4)
FOXTROT-FK-P-PFD-6001~82A (Option 1~4)
FOXTROT-FK-P-PFD-6001D~82A (Demolition) (Option 1~4)
2 | TRM DWE-PHE ONWJ-350/003 | FOXTROT-FXEA-P-HMB-6101 |  | Heat and Material Balance (HMB) |  | 2021-10-01 | IFR
HMB FXEA (Option 1~4)
HMB FK (Option 1~4)
1 | TRM DWE-PHE ONWJ-350/004 | FOXTROT-O-RPT-1104 |  | Preliminary Line Sizing |  | 2021-10-06 | IFR
2 | TRM DWE-PHE ONWJ-350/005 | FOXTROT-O-RPT-1103 |  | Adequacy Check FXEA Flatform |  | 2021-10-08 | IFR
1 | TRM DWE-PHE ONWJ-350/006 | FOXTROT-O-RPT-1101 |  | Equipment Sizing Report |  | 2021-10-11 | IFR
2 | TRM DWE-PHE ONWJ-350/006 | FOXTROT-M-LST-1101 |  | Equipment List for New Equipment |  | 2021-10-11 | IFR
3 | TRM DWE-PHE ONWJ-350/007 | FOXTROT-FXEA-M-EQL-5101 |  | EQL for new platform (4 Option) |  | 2021-10-13 | IFR
1 | ITS-PEP-IMDZ13-TR-2026-0011 | W2026I-DNGF-EM-100-PRG-WLY-0011 |  | Weekly Report |  | 2026-07-02 | IFR
ELECTRICAL & INSTRUMENTATION ENGINEERING (as of 2 October)
[9 empty] | 91.76% | 84.94%
100%
[9 empty] | 91.21% | 89.34%
68.5%

## Appendix D
PERTAMINA EP
| Project Title : | Document Number :
| Integrated Management Dashboard Production & Project Zona 13 | W2026I-DNGF-EM-100-PRG-WLY-0012
| Document Title: | Appendix C
Weekly Report
APPENDIX D
ACTIVITY DOCUMENTATION WEEK 11

## Activity Documentation
PERTAMINA EP
|  |  | Project Title : | Document Number : | W2026I-DNGF-EM-100-PRG-WLY-0012
Integrated Management Dashboard Production & Project Zona 13
Document Title:
Weekly Report
ACTIVITY DOCUMENTATION WEEK 11
| DATE | ACTIVITY | DOCUMENTATION
| 2026-06-28 | Tim ITS telah menyelesaikan 8 menu dashboard sebagaimana pada gambar dibawah mencapai total keseluruhan ketercapaian menu dashboard 88.89%. Untuk 1 menu OSF – AIRMS sedang dalam proses.