## Sheet1
NO. | Rec. No. | NODE NO | REC. NO. | NODE | DEVIATION | POSSIBLE CAUSE | CONSEQUENCES | SAFEGUARD | RECOMMENDATION | LIKELIHOOD | SEVERITY | RISK | RESPONSIBILITY/PIC | TYPE | TARGET DATE | RESPONSE / PROGRESS | CATEGORY | SUB CATEGORY | STATUS | EVIDENCE | COMPLETION DATE | SME
1 (contoh) | 1.1. | 1 | 1 | 01 - Receiving Facilities (Production Well to Flowlines until Manifold Station) | No/ Less/ Low Flow Note: - Experienced miscommunication of bean up/bean down - Flowline Not yet pigged since start up as flow performance is OK | Malfunction close of 210 SDV 1103, 1203, 1303, 1403, 1503, 1603, 1703, 1803, 1903 downstream of choke valve | Potential loss of production from respective well. Potential high pressure wellstream upstream of 210 SCSSV 1X01, up to well SITP (around 2600 psig). No significant safety concern because the well string is designed for API 5000 (design pressure more than 3000 psig). Segment upstream SDV 1X03 is rated ANSI 1500# which can withstand up to 3705 @ 100F | Prevention 1. PM Program for10 SDV 1103, 1203, 1303, 1403, 1503, 1603, 1703, 1803, 1903 is part of wireline and testing program 2. Pipeline upstream of 10 SDV 1103, 1203, 1303, 1403, 1503, 1603, 1703, 1803, 1903 is fully rated (ANSI 1500#, 3705 psig@100F) Note: - The following safeguard is actually available but not effective due to currently not active (bypassed for all Donggi wells) : 210 PSHH 1102A A/B, 1202 A/B, 1302 A/B, 1502 A/B, 1602 A/B, 1702 A/B, 1802 A/B, 1902 A/B, to close 210 SCSSV 1101 and 210 SSV 1102, 1202, 1302, 1403, 1502, 1602, 1702, 1802, 1902. Mitigation 1. 210 ZIC 1103A, 1203A, 1303A, 1403A, 1503A, 1603A, 1703A, 1803A, 1903A (Valve position indicator) can be seen from DCS 2. 210 PSLL 1102, 1202, 1302, 1402, 1502, 1602, 1702, 1802, 1902 A A/B to close 10 SCSSV and SSV of respective well. | Consider to formalize the deactivation of 210 PSHH 1102A A/B, 1202 A/B, 1302 A/B, 1502 A/B, 1602 A/B, 1702 A/B, 1802 A/B, 1902 A/B, to close 210 SCSSV 1101 and 210 SSV 1102, 1202, 1302, 1403, 1502, 1602, 1702, 1802, 1902 through proper MoC process including its associated risk assessment to justify that elimination of this layer of protection does not result in unacceptable risk (May consider to conduct LOPA). If the LOPA study concludes that the available safeguards (apart from the 210 PSHH 1X02 A/B which is being bypassed) are adequate to mitigate the risk of overpressurization of the whole flowline then the PSHH may be removed. Note: - SITP for the respective well must be confirmed when conducting the LOPA | 2 | 1 | 2 | OSF (PS) | STUDY | 2022-12-31 | LOPA Workshop has been conducted on 12 - 16 Dec 2022. |  | STUDY | CLOSED |  | 2022-12-16