## Sheet1
NO. | NODE NO | REC. NO. | NODE | GUIDEWORD | HAZARD | CONSEQUENCES | SAFEGUARD | RECOMMENDATION | LIKELIHOOD | SEVERITY | RISK | RESPONSIBILITY/PIC | TYPE | TARGET DATE | RESPONSE / PROGRESS | CATEGORY | SUB CATEGORY | STATUS | EVIDENCE | COMPLETION DATE
1 (contoh) | 1 | 1 | 01 - Wellhead and Flowline System – production wells and water injection wells | Blow-out | 1. Emergency case and maintenance activity 1. Well Intervention | 1. Excess of toxic and HC release, leading to fire if ignited, personnel injury/fatalities | 1. BOP is provided during well intervention 2. Well Intervention procedure 3. Certified well service vendor 4. Kick off separator provided by well service vendor during well intervention activity 5. F&G detectors are available in wellpad area to stop production and monitor at CCR 6. SCBA (Self Containted Breathing Apparatus) 7. ERP 8. Communication tools 9. MoU for emergency agreement with adjacent Oil & Gas Company 10. Portable fire extinguisher | To provide MoU for medical evacuation with well-known insurance and hospital | 2 | 5 | 10 | Health/HSSE | OTHER | 2023-12-31 | MOUs with hospitals in Luwuk are available: RS Claire Medika Luwuk, RS Pertamedika IHC, RSUD Luwuk Kabupaten Banggai. | Health |  | CLOSED |  | 2023-10-09