## Sheet1
NO. | FUNCTION NO. | FUNCTION NAME | FUNCTION DESCRIPTION | FINAL ELEMENT | RECOMMENDATION | RRF GAP VALUE | RRF GAP TYPE | RESPONSIBILITY/PIC | TARGET DATE | REMINDER STATUS | RESPONSE / PROGRESS | STATUS | EVIDENCE | COMPLETION DATE
1 | LOPA-01 | 310-PAHH-10XX | Pressure High-High at production manifold and test manifold |  | Layer of protection for well-test operation is considered insufficient, due to routine activity of well-test operation triggering High ICL. The following option is recommended to be done: 1. Change well-test operation frequency from routine activity to non-routine activity (less than once per year). If it is agreed to change well-test operation to non-routine activity, then upgrading existing High-High Pressure SIF to SIL 3 or installing additional High-High Pressure with SIL requirement of SIL 1 is considered enough. 2. If well-test operation is kept as routine activity, then it is recommended to: a). Install PSV at each flowline to protect flowline downstream SDVs, or b). Install additional High-High Pressure SIF with SIL requirement of SIL 2. The new SDV shall be installed at upstream 310-SDV-10X3, or c). Modify well-test operation mode from manual operation to automatic operation by installing automatic well switching system. If it is agreed to modify well-test operation mode, then upgrading existing High-High Pressure SIF to SIL 3 or installing additional High-High Pressure with SIL requirement of SIL 1 is still required. | 300.3 | 100 ≤ RRF < 1000 | OSF | 2025-12-31 | MEDIUM HIGH | Study required in 2023 to select those LOPA result’s option MOC required at Q2 2023 Execution as ABI NBD 2024: 1. To apply interlock system during well test to eliminate initiate cause event of inadvertent closure of manual valve at upstream production separator and test separator isolation valves) -> MOC pemilihan mechanical interlock done. Tim OSF sedang melakukan re-assessment terkait mechanical interlock dibandingkan dengan automatic well switching system. 2. To develop SOP accordingly. | ON PROGRESS
2 | LOPA-02 | 320-PAHH-1003 | Pressure High-High at HP Separator | To close all Process SDV's; Shutdown Booster Compressor System; Shutdown AGRU Unit; Shutdown BSRU Unit; Shutdown HP Fuel Gas System; Shutdown Dehydration Unit; Initiate USD Action | Layer of protection for this scenario is considered insufficient. Consider to reactivate the PSD at HP Separator by the 320-PAHH-1003. Having 320-PAHH-1003 activated, the RRF Gap of this scenario will be reduced from 49.5 to 9 (RRF Gap Target <10). | 49.5 | 10 ≤ RRF < 100 | OSF | 2024-12-31 | LOW | MOC cycle due date (MTDF-EM-320-MOC-0001): Inisiasi: 6 Jan 2023 Skrining: W1 June 2023 Engineering Recommendation: 14 Aug 2023 Eksekusi: Close Out MOC: Dec 2024 Telah diaktivasi. MOC Closing sedang ongoing | CLOSED
3 | LOPA-03 | 320-LAHH-1004 | Level High-High at HP Separator Condensate Compartment | To close all Process SDV's; Shutdown Booster Compressor System; Shutdown AGRU Unit; Shutdown BSRU Unit; Shutdown HP Fuel Gas System; Shutdown Dehydration Unit; Initiate USD Action | Layer of protection for this scenario is considered insufficient. It is recommended to reactivate 320-LAHH-1004 at HP Separator and 381-LAHH-1005 at Flare KO Drum. Having both SIS activated, RRF Gap for this scenario will be reduced from 315 to 3.2. | 315 | 100 ≤ RRF < 1000 | OSF | 2024-12-31 | LOW | 320-LAHH-1004 is activated (53/ORA/MTD/XI/2022). In addition, 381-LAHH-1005 wil be activated by voting through MOC cycle due date: Inisiasi: 2 minggu ( 24 Mar 2023) Skrining: 2 minggu (2 Apr 2023) Engineering Recommendation: W4 Jun 2023 Eksekusi: TAR 2024 Close Out: Dec 2024 MOC No. MTDF-EM-381-MOC-0018 sedang dilakukan pengumpulan data selama 3 bulan untuk melihat fluktuasi, jika banyak kejadian maka akan dieksekusi. Jika tidak maka MOC void. --> DONE diaktivasi di TA tanpa resetting. Menunggu ORA Form pelepasan override dari lapangan | CLOSED |  | 2024-10-21
4 | LOPA-06 | 320-PAHH-1012 | Pressure High-High at Test Separator | To close 320-SDV-1012 Flow to Test Separator | Layer of protection for this scenario is considered insufficient. Consider to reactivate the PSD at Test Separator by the 320-PSHH-1012. Having 320-PSHH-1012 activated, the RRF Gap of this scenario will be reduced from 90 to 9 (RRF Gap Target <10). | 90 | 10 ≤ RRF < 100 | OSF | 2024-12-31 | LOW | MOC cycle due date (MTDF-EM-320-MOC-0002): Inisiasi: 6 Jan 2023 Skrining: W1 June 2023 Engineering Recommendation: 14 Aug 2023 Eksekusi: Close Out MOC: Dec 2024 Telah diaktivasi. Closing MOC ongoing | CLOSED |  | 2024-10-21
5 | LOPA-13 | 330-LALL-1004A/B | Level Low-Low at Gas Liquid Coalescer |  | Layer of protection for this scenario (gas blowby from Gas Liquid Coalescer to Closed Drain Drum) is considered insufficient. The following modification are recommended to be done: 1. Ensure 377-PSV-1001 at Closed Drain Drum can handle gas blowby flow rate from Gas Liquid Coalescer. Otherwise, replace the existing PSV size with the proper one or install Restriction Orifice (RO) to limit gas blowby rate below PSV capacity. 2. Put 330-LV-1005A/B in manual mode and in closed position to eliminate this scenario of gas blowby (through 330-LV-1005A/B) to closed drain drum. If this Level Control Valve is kept in automatic mode, then remove override/inhibit of SIF 330-LALL-1003A/B at Gas Liquid Coalescer bottom compartment. | 3300 | 1000 ≤ RRF < 10.000 | OSF | 2024-06-30 | LOW | 1. 377-PSV-1001 adequacy check has been performed and PSV is adequate for gas blowby case. -> 377-PSV-1001 is adequate to handle gas blowby rate from 330-LV-1005, as per Doc. No. GDMF-PR-200-TEN-0001. 2. MOC No. MTDF-EM-330-MOC-0004 Inisiasi: 8 Feb 23 Screening: 4 Mei 23 Technical Meeting: 5 Mei 23 ER: W4 Jun 23 Execution: Dec 23 Close out MOC: Jan 24 ORA Closing No. 4/ORA/MTD/2022/E-10 | CLOSED |  | 2023-11-07
6 | LOPA-18 | 350 LALL 1005 | Level Low-Low at Glycol Contactor | To close 350-SDV-1003 Rich Glycol to Reflux Condenser (350-E-1002) | Layer of protection for this scenario (gas blowby from Glycol Contactor to Glycol Flash Drum) is considered insufficient. The following recommendation need to be done: 1. Ensure 350-PSV-1110 at Glycol Flash Drum (sized for Fire Case) can handle the gas blowby flow rate from Glycol Contactor through 350-LV-1002. Otherwise, replace the existing PSV size with the proper one or install Restriction Orifice (RO) to limit gas blowby rate below PSV capacity. 2. Ensure capacity of 350-PCV-1104 at Glycol Flash Drum can handle the gas blowby rate from Glycol Contactor through 350-LV-1002. Otherwise, install Restriction Orifice (RO) to limit gas blowby rate below PCV capacity. | 1500 | 1000 ≤ RRF < 10.000 | OSF | 2025-06-30 | CLOSED | Study has been reported in Doc. No. GDMF-PR-200-TEN-0001. 1. The 350-PSV-1110 is designed based on fire case. However, this orifice which has capacity of 2760 lb/hr or 1.42 MMscfd @Pset 130 psig can also handle gas blowby rate through 350-LV-1002. 2. Capacity 350-PCV-1104 at Cv max and 75 psig (max op. pressure) is est. 1159 lb/hr or 0.6 MMscfd, which means it is adequate to handle maximum gas blowby rate through 350-LV-1002. No modification is required. | CLOSED |  | 2023-11-07
7 | LOPA-20 | 320-PAHH 1013 | Pressure High-High at LP Separator | To close 320-SDV-1014 Cond. Outlet from Test Separator; 320-SDV-1004 Cond. Outlet from HP Separator; 320-SDV-1009 Cond. Outlet from HP Scrubber; 320-SDV-1034 Cond. Outlet from Wash Tower; 330-SDV-1004A/B liquid outlet from Booster Compressor Suction Drum A/B; and to trip Closed Drain Pump A/B, Flare KO Pump A/B, Acid Flare Pump A/B | Layer of protection for this scenario is considered insufficient. The following modification is recommended to be done: 1. Reactivate SIF of Low-Low Level at equipment upstream of LP Separator, to prevent gas blowby scenario from upstream to LP Separator, and 2. Provide an independent High Pressure Alarm at LP Separator for operator response, or 3. Upgrade integrity level of 320-PAHH-1013 at LP Separator from SIL 1 to SIL 2 e.g. by increasing frequency of SIF loop function test. Note: One of point no. 2 or point no. 3 can be selected with reactivation of SIS as mentioned in point no. 1 (option that can be selected: point no. 1 & 2 or point no. 1 & 3). | 34.5 | 10 ≤ RRF < 100 | OSF | 2025-12-31 | MEDIUM HIGH | Modification of additional alarm high pressure at LP Separator through MOC -> OSF Dec 24 | ON PROGRESS
8 | LOPA-21 | 320-LALL-1008 A | Level Low-Low at LP Separator Condensate Compartment | To close 380-SDV-1001 Cond. Outlet from Condensate Coalescer and 380-SDV-1007 Water Outlet from Condensate Coalescer | Layer of protection of this scenario is considered insufficient. It is recommended to conduct further study for providing additional IPL: 1. To study the adequacy of 380-PV-1001 at Condensate Stabilizer in handling gas blowby from 320-LV-1007A. 2. To study possibility of taking credit 380-PSV-1223A/B at Condensate Preheater by resetting PSV set point and reducing operating pressure. Currently, 380-PSV-1223A/B set point is higher than design pressure of Condensate Stabilizer. 3. If 380-PSV-1223A/B cannot be taken credit following the process study above, then it is proposed to : (a.) Install mechanical stopper at 320-LV-1007A to limit gas blowby flow rate able to be handled by 380-PSV-1215 at Condensate Stabilizer (PO Preference), or (b.) Install Restricted Orifice (RO) downstream of 320-LV-1007A to limit gas blowby flow rate able to be handled by 380-PSV-1215 at Condensate Stabilizer. | 300 | 100 ≤ RRF < 1000 | OSF | 2024-12-31 | LOW | 1. To study the adequacy of 380-PV-1001 at Condensate Stabilizer in handling gas blowby from 320-LV-1007A -> OSF Dec 23 -> 380-PV-1001 is not adequate (Doc. No. GDMF-PR-200-TEN-0001). 2. To check adequacy of 380-PSV-1223A/B -> OSF Dec 23 -> 380-PSV-1223A/B is not adequate (Doc. No. GDMF-PR-200-TEN-0001). 3. Resetting 380-PSV-1223A/B -> OSF Jun 24 4. To review feasibility for option 3.a to 3.b and execution by MOC -> OSF 30 Jun 24 to check 5. Update SOP Maintenance for RO -> OSF & RAM Dec 24 | CLOSED | Based on BA PHA Tahun 2025 | 2025-06-30
9 | LOPA-23 | 320-LAHH-1008 | Level High-High at LP Separator Condensate Compartment | To close 320-SDV-1014 Cond. Outlet from Test Separator; 320-SDV-1004 Cond. Outlet from HP Separator; 320-SDV-1009 Cond. Outlet from HP Scrubber; 320-SDV-1034 Cond. Outlet from Wash Tower; 330-SDV-1004A/B liquid outlet from Booster Compressor Suction Drum A/B; and to trip Closed Drain Pump A/B, Flare KO Pump A/B, Acid Flare Pump A/B | Layer of protection for this scenario is considered insufficient. It is recommended to reactivate 320-LAHH-1008A at LP Separator and 381-LAHH-1006 at Acid Flare KO Drum. Having both SIS activated, RRF Gap for this scenario will be reduced from 330 to 3.3. | 330 | 100 ≤ RRF < 1000 | OSF | 2024-12-31 | LOW | 320-LAHH-1008A is bypassed (ST) due to temporary operating condition, requires study. 381-LAHH-1006, MOC cycle due date: Inisiasi: 2 minggu ( 24 Mar 2023) Skrining: 2 minggu (2 Apr 2023) Engineering Recommendation: W4 Jun 2023 Eksekusi: TAR Aug 2024 Close Out: Dec 2024 MOC No. MTDF-EM-381-MOC-0017 --> DONE diaktivasi di TA tanpa resetting. | ON PROGRESS |  | 2024-10-21
10 | LOPA-24 | 380-LAHH-1003 | Level High-High at Condensate Stabilizer and Reboiled Condensate Drum | To close 380-SDV-1001 Cond. Outlet from Condensate Coalescer; 380-SDV-1006 Condensate Stabilizer gas outlet; and to trip 380-V-1002 Condensate Stabilizer Package | Layer of protection for this scenario is considered insufficient. It is recommended to remove override/inhibit of 381-LAHH-1006 at Acid Flare KO Drum. | 46.5 | 10 ≤ RRF < 100 | OSF | 2024-12-31 | LOW | 381-LAHH-1006, MOC cycle due date: Inisiasi: 2 minggu ( 24 Mar 2023) Skrining: 2 minggu (2 Apr 2023) Engineering Recommendation: W4 Jun 2023 Eksekusi: TAR Aug 2024 Close Out: Dec 2024 MOC No. MTDF-EM-381-MOC-0017 --> DONE diaktivasi di TA tanpa resetting. | CLOSED |  | 2024-10-21
11 | LOPA-25 | 378-PAHH-1002 | Pressure High-High at Produced Water Stripper | To close 378-SDV-1001 Fuel Gas to PW Stripper; 320-SDV-1006 flow from HP PW Filters; 320-SDV-1007 flow from LP PW Filters; 320-SDV-1013 PW from Test Separator; 320-SDV-1033 PW from Wash Tower; 380-SDV-1007 flow from Condensate Coalescer | Layer of protection of this scenario is considered insufficient. The following modification is recommended to be done: 1. Relocate tie in point of pressure transmitter 378-PT-1002 to upstream demister of PW Stripper. 2. Provide additional high pressure alarm at upstream 378-PV-1001A/B for operator response 3. Remove override/inhibit for Low-Low Level SIS at upstream equipment. | 61.5 | 10 ≤ RRF < 100 | OSF | 2024-12-31 | LOW | Proposed in TAR Scope 2024, to check demister of Produced Water Stripper. If it's clean, the scenario is not credible and the recommendation will not be applicable. <- MOC is not needed since GAMMA Test result shows no deposit at Demister of Test Separator | CLOSED |  | 2024-06-03
12 | LOPA-27 | 370-PALL-1007 | Pressure Low-Low at HP Fuel Gas Scrubber | To close all Process SDV's; Shutdown Booster Compressor System; Shutdown AGRU Unit; Shutdown BSRU Unit; Shutdown HP Fuel Gas System; Shutdown Dehydration Unit; Initiate USD Action | Layer of protection for this scenario is considered insufficient. Consider to provide additional independent High Pressure Alarm at HP Fuel Gas Scrubber for operator response | 100.2001 | 100 ≤ RRF < 1000 | OSF | 2024-12-31 | LOW | Proposed in TAR 2024 scope. Inisiasi: 2 minggu ( 24 Mar 2023) Skrining: 2 minggu (2 Apr 2023) Engineering Recommendation: W4 Jun 2023 Eksekusi: DCS 2023 Close Out: Dec 2023 MOC No. MTDF-EM-370-MOC-0010 Override on 370-PZI-1007 has been closed. | ON PROGRESS | OSF to send the evidence | 2023-09-26
13 | LOPA-28 | 370-PAHH-1007 | Pressure High-High at HP Fuel Gas Scrubber | To close 370-SDV-1003 back-up of fuel gas source and 370-SDV-1004 flow from Gas/Gas Exchanger | Layer of protection for this scenario is considered insufficient. It is recommended to remove override/inhibit of SIF 370-PAHH-1007 at HP Fuel Gas Scrubber. | 37.5 | 10 ≤ RRF < 100 | OSF | 2024-12-31 | LOW | Proposed in TAR 2024 scope. Inisiasi: 2 minggu ( 24 Mar 2023) Skrining: 2 minggu (2 Apr 2023) Engineering Recommendation: W4 Jun 2023 Eksekusi: DCS 2023 Close Out: Dec 2023 MOC No. MTDF-EM-370-MOC-0010 MOC to cover removal of override 370-PAHH-1007 | CLOSED |  | 2023-09-26
14 | LOPA-29 | 370-LALL-1001 | Level Low-Low at HP Fuel Gas Scrubber | To close 370-SDV-1001 liquid outlet from HP Fuel Gas Scrubber | Layer of protection for this scenario (gas blowby from HP Fuel Gas Scrubber to Closed Drain Drum) is considered insufficient. The following modification are recommended to be done: 1. Ensure 377-PSV-1001 at Closed Drain Drum can handle gas blowby flow rate from HP Fuel Gas Scrubber. Otherwise, replace the existing PSV size with the proper one or install Restriction Orifice (RO) to limit gas blowby rate below PSV capacity, or 2. Put 370-LV-1002 in manual mode and in closed position (as no liquid build up during normal operation) to eliminate this scenario of gas blowby (through 370-LV-1002) to closed drain drum. | 150 | 100 ≤ RRF < 1000 | OSF | 2024-12-31 | CLOSED | PSV adequacy check has been conducted and reported in Doc. No. GDMF-PR-200-TEN-0001. Based on the result, The capacity of the 377-PSV-1001 is still adequate, so there is unnecessity to install additional Restriction Orifice (RO) at downstream 370-LV-1002 of HP Fuel Scrubber, 370-LV-1008 of LP Fuel Scrubber and Air Trap SP-08-1001/1002/1003/1004 of HP and LP Fuel Filter drain line and also the 370-LV-1002 and 370-LC-1008 still can be put in automatic position during normal operation. | CLOSED |  | 2023-11-07
15 | LOPA-30 | 370-TAHH-1002/1017 | Temperature High-High at Fuel Gas Electric Heater | To trip Fuel Gas Electric Heater UCP and to close 370-SDV-1005A/B Fuel Gas to Fuel Gas Electric Heater A/B | Layer of protection for this scenario is considered insufficient. It is recommended to remove override/inhibit of SIF 370-TAHH-1002/1017 at Electric Heater. | 15 | 10 ≤ RRF < 100 | OSF | 2024-12-31 | LOW | Proposed in TAR 2024 scope. Inisiasi: 6 Jan 2023 Skrining: 9 May 2023 Engineering Recommendation: 9 May 2023 Eksekusi: DCS 2023 Close Out: Dec 2023 MOC No. MTDF-EM-370-MOC-0011/12 | CLOSED |  | 2023-09-26
16 | LOPA-32 | 370-LALL-1007 | Level Low-Low at LP Fuel Gas Scrubber | To close 370-SDV-1007 liquid outlet from LP Fuel Gas Scrubber | Layer of protection for this scenario (gas blowby from LP Fuel Gas Scrubber to Closed Drain Drum) is considered insufficient. The following modification are recommended to be done: 1. Ensure 377-PSV-1001 at Closed Drain Drum can handle gas blowby flow rate from LP Fuel Gas Scrubber. Otherwise, replace the existing PSV size with the proper one or install Restriction Orifice (RO) to limit gas blowby rate below PSV capacity, or 2. Put 370-LV-1008 in manual mode and in closed position (as no liquid build up during normal operation) to eliminate this scenario of gas blowby (through 370-LV-1008) to Closed Drain Drum. (Chosen option) | 150 | 100 ≤ RRF < 1000 | OSF | 2024-12-31 | CLOSED | PSV adequacy check has been conducted and reported in Doc. No. GDMF-PR-200-TEN-0001. Based on the result, The capacity of the 377-PSV-1001 is still adequate, so there is unnecessity to install additional Restriction Orifice (RO) at downstream 370-LV-1002 of HP Fuel Scrubber, 370-LV-1008 of LP Fuel Scrubber and Air Trap SP-08-1001/1002/1003/1004 of HP and LP Fuel Filter drain line and also the 370-LV-1002 and 370-LC-1008 still can be put in automatic position during normal operation. | CLOSED |  | 2023-11-07
17 | LOPA-33 | 381-LAHH-1005 | Level High-High at Flare KO Drum | To close all Process SDV's; Shutdown Booster Compressor System; Shutdown AGRU Unit; Shutdown BSRU Unit; Shutdown HP Fuel Gas System; Shutdown Dehydration Unit; Initiate USD Action | Layer of protection for this scenario is considered insufficient. It is recommended to remove override/inhibit of SIF 381-LAHH-1005 at HP Flare KO Drum. | 30 | 10 ≤ RRF < 100 | OSF | 2024-12-31 | LOW | 381-LAHH-1005 wil be activated by voting through MOC cycle due date: Inisiasi: 2 minggu ( 24 Mar 2023) Skrining: 2 minggu (2 Apr 2023) Engineering Recommendation: W4 Jun 2023 Eksekusi: TAR 2024 Close Out: Dec 2024 MOC No. MTDF-EM-381-MOC-0018 sedang dilakukan pengumpulan data selama 3 bulan untuk melihat fluktuasi, jika banyak kejadian maka akan dieksekusi. Jika tidak maka MOC void. --> DONE diaktivasi di TA tanpa resetting. | CLOSED |  | 2024-10-21
18 | LOPA-34 | 381-LAHH-1006 | Level High-High at Acid Gas Flare Drum | To close all Process SDV's; Shutdown Booster Compressor System; Shutdown AGRU Unit; Shutdown BSRU Unit; Shutdown HP Fuel Gas System; Shutdown Dehydration Unit; Initiate USD Action | Layer of protection for this scenario is considered insufficient. It is recommended to remove override/inhibit of SIF 381-LAHH-1006 at Acid Flare KO Drum. | 30 | 10 ≤ RRF < 100 | OSF | 2024-12-31 | LOW | 381-LAHH-1006, MOC cycle due date: Inisiasi: 2 minggu ( 24 Mar 2023) Skrining: 2 minggu (2 Apr 2023) Engineering Recommendation: W4 Jun 2023 Eksekusi: TAR 2024 Close Out: Dec 2024 MOC No. MTDF-EM-381-MOC-0017 sedang dilakukan pengumpulan data selama 3 bulan untuk melihat fluktuasi, jika banyak kejadian maka akan dieksekusi. Jika tidak maka MOC void. | CLOSED |  | 2024-10-21
19 | LOPA-35 | 377-LAHH-1001 | Level High-High at Closed Drain Drum | To close 330-SDV-1005A/B Drain from Gas Liquid Coalescer, 370-SDV-1001 Drain from HP Fuel Gas Scrubber, 370-SDV-1007 Drain from LP Fuel Gas Scrubber; and to trip Drain HC Pump 340-P-1016 | Layer of protection for this scenario is considered insufficient. It is recommended to remove override/inhibit of SIF 381-LAHH-1006 at Acid Flare KO Drum. | 15 | 10 ≤ RRF < 100 | OSF | 2024-12-31 | LOW | 381-LAHH-1006, MOC cycle due date: Inisiasi: 2 minggu ( 24 Mar 2023) Skrining: 2 minggu (2 Apr 2023) Engineering Recommendation: W4 Jun 2023 Eksekusi: TAR Aug 2024 Close Out: Dec 2024 MOC No. MTDF-EM-381-MOC-0017 --> DONE diaktivasi di TA tanpa resetting. | CLOSED |  | 2024-10-21
20 | LOPA-36 | 377-PALL-IIII | Pressure Low-Low at Closed Drain Drum |  | Layer of protection for this scenario is considered insufficient. Consider to install vacuum breaker at Closed Drain Drum as additional IPL for this scenario. | 300 | 100 ≤ RRF < 1000 | OSF | 2025-12-31 | MEDIUM HIGH | To study potential occurrence of vacuum condition at close drain drum in Dec 2023 Execution as MOC 2024 | CLOSED | Based on BA PHA Tahun 2025 | 2025-06-30
21 | LOPA-37 | 377-PAHH-BBBB | Pressure High-High at Closed Drain Drum |  | Layer of protection for this scenario (overpressurization in Closed Drain Drum) is considered insufficient. Ensure 377-PSV-1001 at Closed Drain Drum can handle gas blowby flow rate from upstream equipments. Otherwise, replace the existing PSV size with the proper one or install Restriction Orifice (RO) to limit gas blowby rate below PSV capacity. | 195 | 100 ≤ RRF < 1000 | OSF | 2023-12-31 | CLOSED | PSV adequacy check has been conducted and reported in Doc. No. GDMF-PR-200-TEN-0001. Based on the result, The capacity of the 377-PSV-1001 is still adequate, so there is unnecessity to install additional Restriction Orifice (RO) at downstream 370-LV-1002 of HP Fuel Scrubber, 370-LV-1008 of LP Fuel Scrubber and Air Trap SP-08-1001/1002/1003/1004 of HP and LP Fuel Filter drain line and also the 370-LV-1002 and 370-LC-1008 still can be put in automatic position during normal operation. | CLOSED |  | 2023-11-07
22 | LOPA-40 | 340-PAHH-CCCC | Pressure High-High between Amine Booster Pump and Amine Pump |  | Layer of protection for this scenario is considered insufficient due to pipe rating in between Amine Pump and Amine Booster Pump is #150 only. The following recommendation needs to be done: 1. Conduct a feasibility study for Amine Booster Pump impeller modification (impeller size reduction) to achieve pump shut-off pressure less than the pipe rating of #150 and implement the modification accordingly (if the study result shows the modification is feasible). Note: Having pump impeller modification (impeller size reduction), this scenario of overpressure at Amine Booster Pump discharge due to a blocked outlet is no more credible. Thus, recommendation point no. 4 can be dropped out from this recommendation list. 2. Install High-High Pressure SIF with SIL requirement of SIL 1 in between Amine Pump and Amine Booster Pump. 3. Provide additional independent High Pressure Alarm in between Amine Pump and Amine Booster Pump for operator response. 4. In case pump impeller modification is not feasible, install PSV in between Amine Pump and Amine Booster Pump to handle blocked discharge scenario or gas reverse flow from Acid Gas Absorber (which one the highest flow rate). | 60150 | 10.000 ≤ RRF < 100.000 | OSF | 2024-12-31 | CLOSED | Feasibility study for Amine Booster Pump 340-P-1002A/B has been reported in Doc. No. GDMF-PR-200-TEN-0001. This recommendation will not be fulfilled considering: a. MAWP of the existing equipment & piping is still higher than pump shut off pressure (fully mechanical rating) b. Take credit the existing BPCS minimum flow control valve to anticipate the pump falls to shut off condition. The flowmeter indicator sited in pump discharge line is equipped with Hi-Lo alarm to alert the operator. c. Take credit the existing PAH at 340-PI-1011 at top of Amine Stripper Column as safeguard to preventextreme discharge pressure at pump discharge (avoid set 340-PSV-1066 is reached resulting liquid release to acid flare). The alarm H will alert the operator. And if this credit is added as safeguard to the LOPA worksheet, the RRF obtained is 6, which is less than criteria RRF=10, which means adequate. | CLOSED |  | 2023-11-07